## Feature Tracker
FACTORY OS · FEATURE CHANGE LOG
Simple call record · 15–20 August 2026 · One row per feature or correction
TOTAL CHANGES |  | DATES COVERED |  | LATEST CALL DATE |  | LOG FORMAT
30 |  | 15–20 August 2026 |  | 2026-08-20 |  | One row per change
Change ID | Date | Tab / Area | Feature requested | What was corrected / changed | How it was tested | Test result | Follow-up / notes
| 21 st Aug |  | Create a customer centric UI: MIS: - show total orders, orders on time, delayed, orders at risk, dates for each type; order vs dispatch shortfall for the last month; avg production days; capacity utilisation percentage
| 21 st Aug |  | Its breaking the order per line/not beign able to read it properly
| 21 st Aug |  | Input sheet for complete update on each machine, production, live plans and actual production -- with feedback and showing order pipeline changes
| 21 st Aug |  | Catalogie should be editable for all categories — eg gola plus should be
| 21 st Aug |  | Link scheduling to PI database
CHG-001 | 2026-08-20 | PI generation | Generate PI after Match & Check edits | Added an explicit Generate PI action that snapshots the latest checked values into the invoice. | Browser workflow: entered an order, edited fields and generated the PI. | PI rendered from the edited values. | Use Regenerate whenever Match & Check changes.
CHG-002 | 2026-08-20 | PI generation | Regenerate PI when checked data changes | The app detects when a generated PI is stale, shows a warning and disables Print/Save until regeneration. | Browser workflow: changed Upper Colour after generating a PI. | Stale warning appeared; Save was disabled; Regenerate was available. | Prevents an old PI being sent after edits.
CHG-003 | 2026-08-20 | PI generation | Retain draft while changing tabs | PI intake remains mounted while navigating, so photos, rows and edits stay until Save or Close PI. | Browser workflow: edited a draft, visited Packing & BOM Rules, returned to PI generation. | Draft and edited value remained intact. | Close PI explicitly discards the draft.
CHG-004 | 2026-08-20 | PI generation | Create a new PI after edits | Added Generate Again and New PI Number actions after Match & Check corrections. | Browser UI verification and production build. | Controls rendered and PI number can be refreshed. | PI save still requires complete article details.
CHG-005 | 2026-08-20 | Match & Check | Remove Party & Article Defaults block | Removed the initial global defaults section; customer and article details now live on each item row. | Browser visual inspection and production build. | Opening defaults block is gone; item-level fields are visible. | Matches the one-item-per-order-sheet workflow.
CHG-006 | 2026-08-20 | Match & Check | Per-article customer and order fields | Added Customer, City, Order Date, Priority, Order Nature, V/L, Sole Colour, Upper Colour, Print and Stitching to every article. | Browser form inspection and PI generation test. | Values appeared per item and flowed to the PI. | No new database columns required.
CHG-007 | 2026-08-20 | Match & Check | Article/type change recalculates packing | Changing article or V/L remaps valid combos and immediately recalculates pairs per carton. | Browser test: SPIKE Lace → SPADE Lace. | Ranges changed from 6X8/9X12 to 6X7/8X12 and packing remained 18 pairs/carton. | Old pairs/carton is not retained after an article change.
CHG-008 | 2026-08-20 | Packing & BOM rules | SPIKE follows ARMOUR packing | SPIKE resolves its packing by matching range position to ARMOUR, including differently named Lace ranges. | Automated unit tests for 7X10S and SPIKE 6X8 → ARMOUR 6X9. | Inheritance tests passed. | Editing SPIKE writes to the ARMOUR source range.
CHG-009 | 2026-08-20 | Packing & BOM rules | Show packing list for every article/type | Added article/type selector with size range, interpreted PI sizes and pairs/carton. | Browser inspection across the new Setup tab. | Packing table displayed the effective values used by PI and order logic. | Also visible inside each Match & Check card.
CHG-010 | 2026-08-20 | Packing & BOM rules | Show BOM for every article/type | Added a per-combo BOM matrix showing stage, material/UOM and rate per pair. | Browser inspection and source-data extraction across all article types. | BOM matrix rendered; missing BOM is shown instead of estimated. | REX GOLA PLUS currently has packing but no BOM on file.
CHG-011 | 2026-08-20 | Packing & BOM rules | Edit pairs per carton in the rules tab | Pairs/carton cells are editable with Save and Discard controls; saved changes feed all later orders and PIs. | Browser test: changed SPIKE 7X10S from 24 to 25, confirmed Save/Discard enabled, then discarded and restored 24. Automated source-mapping test passed. | Editor controls work locally; production database write still needs deployment verification. | Latest local change; push to GitHub before Vercel can use it.
CHG-012 | 2026-08-20 | Bulk upload | Read supplied Institutional and MTO Order Book | Importer now recognises customer, city, article, colours, Lace/Velcro, sole, status and repeated individual-size columns. | Parsed Order book 17-07-2026.xlsm directly. | 31 recognised orders, 11,211 pairs and 0 blocking errors. | 57 warnings are unknown catalogue articles and are skipped.
CHG-013 | 2026-08-20 | Bulk upload | Read every workbook sheet and .xlsm files | Bulk upload loops through all workbook sheets and accepts .xlsm in addition to Excel/CSV formats. | Actual workbook test covered INSTITUTIONAL ORDER BOOK and MTO ORDER BOOK (2). | Both sheets parsed successfully. | Warnings do not block recognised rows.
CHG-014 | 2026-08-20 | Bulk upload | One-row-per-article order template | Download template now places all individual sizes across one row with customer/article metadata before them. | Automated importer tests and production build. | New template structure is readable by the importer. | Kids sizes use s; adult sizes use the later numeric columns.
CHG-015 | 2026-08-20 | Orders & dispatch | Edit orders after saving a PI | Saved orders can be reopened, corrected and saved; Save & Produce is also available. | Code validation, automated quantity tests and production build. | Implemented locally; production workflow should be checked once deployed with live data. | No schema migration required for order edits.
CHG-016 | 2026-08-20 | PI database | Master database of issued PIs | Added a PI database screen and server snapshot records so issued/revised PIs remain available independently of live orders. | Automated PI tests and API/build validation. | Implemented; requires the production table to exist. | Run npm run db:setup once if the latest schema has not been applied.
CHG-017 | 2026-08-20 | Parties & terms | Remove dispatch timeline from Parties tab | Removed dispatch-timeline editing/display from the Parties & Terms screen. | Source check and production build. | Field is no longer shown in that tab. | No destructive database migration required.
CHG-018 | 2026-08-20 | Production plan | Remove unnecessary one-day buffer | Removed duplicated in-house preparation/release buffering from scheduling. | Automated engine test: in-house preparation is not counted twice. | Engine test passed. | Outside stitching/printing lead-time rules remain explicit.
CHG-019 | 2026-08-20 | Production plan | Show production-planning logic per order | Schedule/plan views expose stage routing, machine allocation, dates, lead time and delivery risk per order. | Automated engine tests for routing, contention, machine exclusivity and dates. | All engine tests passed. | Planner continues to surface unknown combos rather than guessing.
CHG-020 | 2026-08-20 | Deployment | Vercel and database deployment guidance | Confirmed that GitHub push deploys code, while schema setup must be run separately when required. | Compared working tree, origin/main and db/schema.sql. | Latest packing editor is still local; PI master schema is already present in repository. | Commit/push four latest files; run npm run db:setup if proforma_invoices is absent.
CHG-021 | 2026-08-15 | Parties & terms | List of parties with discount and payment terms non-editable on each PI | The party master stores city, discount, deduction sequence, GST and payment split. Each PI reads these terms and does not permit a separate per-PI override. | Reviewed party and PI logic, API handling and the passing PI test suite. | Implemented; verify permissions and live party records after deployment. | Party-master records remain maintainable through the authorized Parties workflow; they are read-only within an individual PI.
CHG-022 | 2026-08-15 | PI generation / Orders | Ability to add orders in cartons | Added carton-based entry alongside pairs. Pairs are recalculated using the selected article's packing rule and pairs-per-carton value. | Checked the Match & Check workflow and ran the automated size/carton conversion tests. | Carton and pair entry works in automated tests. | Changing the article refreshes pairs per carton from the packing rule before carton totals are calculated.
CHG-023 | 2026-08-15 | Production plan | Add a Preparation machine between Cutting and Stitching | Added an explicit Preparation work centre and route stage for printing and cutting preparation between Cutting and Stitching. | Ran production-engine routing tests and the application build. | Stage order and scheduling logic passed. | Preparation capacity and working hours can be maintained with the other work centres.
CHG-024 | 2026-08-15 | Match & Check / Production plan | Choose in-house or outside stitching and account for printing | Added per-article Print Yes/No and Stitching In-house/Outside controls. In-house work uses preparation time; outside work uses transportation lead time, and printing adds its configured lead time. | Reviewed the per-article form and ran the production-planning engine tests. | Routing and lead-time logic passed. | The choice is captured per article rather than as one order-wide default.
CHG-025 | 2026-08-15 | Production schedule | Add Upper QC and Preparation between Stitching and Molding | Added Upper QC as a distinct stage after Stitching and before Molding; Preparation remains the separate stage before Stitching. | Ran route-order tests in the production engine and built the app. | Stage order passed. | The wording records both requested preparation points while keeping their correct production sequence.
CHG-026 | 2026-08-15 | Machine load | Separate PVC Rotary, PVC Vertical, PU and Stuck-on | Split molding/assembly capacity into PVC Rotary, PVC Vertical, PU and Stuck-on work centres, with routing based on the article's assigned process. | Ran exclusive-machine production tests and checked the work-centre definitions. | Machine bifurcation and routing passed. | Stuck-on is scheduled as assembly; the three molding types are scheduled independently.
CHG-027 | 2026-08-15 | Packing & Dispatch | Separate Packing and Dispatch | Created separate Packing and Dispatch schedule stages and a dedicated Dispatch & Packing workflow. | Ran production scheduling tests and the application build. | Separate stages are working. | Packing completion and physical dispatch can now be tracked separately.
CHG-028 | 2026-08-15 | Packing & Dispatch | Create a dispatch report against each PI and reduce pending quantity | Added PI/order-level packing reports and dispatch history. Pending quantity is calculated as ordered quantity minus dispatched quantity. | Reviewed dispatch API/schema logic and completed a successful app build. | Implemented; needs an end-to-end check against the production database. | A dispatch report affects pending quantities only after it is saved successfully.
CHG-029 | 2026-08-15 | Orders / Size breakdown | Ability to add specific sizes | Added an Add Size control so each article can contain only the required sizes, with quantities entered in pairs or cartons. | Ran the automated size-editing test suite (10/10 passing). | Specific-size creation and quantity handling passed. | Sizes stay attached to the relevant article and BOM/colour combination.
CHG-030 | 2026-08-15 | Packing & Dispatch | Add dispatch status: Partial Complete, Full Complete and Shortage | Added Partial, Full and Shortage report types, including an explicit option to close an order despite a shortage while retaining the dispatch record. | Reviewed dispatch UI, API and schema logic and completed a successful app build. | Implemented; live partial/full/shortage transactions still need production verification. | Closing with shortage removes the remaining quantity from pending while preserving the shortage status for reporting.

## Call Summary
FACTORY OS · CALL SUMMARY
Dates covered | 15–20 August 2026
MAIN CHANGES LOGGED
PI workflow | Match & Check edits can generate or regenerate the PI, and drafts remain while moving between tabs.
Article rules | Packing and BOM are visible per article/type; carton packing can be edited from the same rules tab.
Production planning | Preparation, Upper QC, separate machine types, Packing and Dispatch are represented as distinct stages.
Orders & dispatch | Orders support cartons and specific sizes, and dispatch reports record partial, full or shortage quantities.
Order Book | The supplied Institutional/MTO workbook format is readable and the template uses one row per article.
TESTING NOTES
Automated checks | Production engine, PI, size and order-import test suites passed.
Browser checks | PI regeneration, article remapping, draft retention and packing-rule editing were checked in the browser.
Workbook import | 31 orders and 11,211 pairs were recognised from the supplied .xlsm workbook with no blocking errors.
Next check | Recheck saved packing changes and the complete dispatch flow in the live app.

## How to Use
HOW TO MAINTAIN THIS TRACKER
After each product call, add one row per feature or correction and use the actual call date.
Field | What to enter | Example
Tab / Area | Where the user sees the change | PI generation
Feature requested | Short description of the request | Generate PI after Match & Check edits
What changed | Plain-language description of the correction | Regenerate PI from the latest checked values
How tested | Specific evidence, not only the word tested | Browser workflow and automated test
Test result | What happened during the check | PI showed the edited values
Follow-up | Anything that still needs checking or a decision | Recheck one live dispatch report
Keep each entry short, factual and easy to scan. Add detail only when it helps someone repeat the check.