## Changes
Factory OS Change Log
Tasks are grouped by day. Update owners and Yes/No status on the Live Tracker tab.
Task ID | Date | Changes discussed | Task for | Made yet?
26 Aug 2026 |  |  |  | 3 of 3 done
T-001 | 2026-08-26 | PI generation tab was wrong - reading sizing wrong, not able to edit PI blanks | Diya | Yes
T-002 | 2026-08-26 | Order dispatch not linked to other tabs | Diya | Yes
T-003 | 2026-08-26 | PI database tab errors - ability to delete, sync across tabs, etc. | Diya | Yes
24 Aug 2026 |  |  |  | 0 of 1 done
T-012 | 2026-08-24 | Update catalogue images for all articles | Abhay | No
23 Aug 2026 |  |  |  | 9 of 19 done
T-004 | 2026-08-23 | Add dispatch timeline option per order | Diya | Yes
T-005 | 2026-08-23 | Generate PI is not reloading to latest discount terms | Diya | Yes
T-006 | 2026-08-23 | Edit MRP should be size by size | Diya | Yes
T-007 | 2026-08-23 | Demo how to add BOMs, catalogue pictures and packing lists | Diya | Yes
T-008 | 2026-08-23 | Treat L as Large; keep Lace and Velcro separate | Diya | Yes
T-009 | 2026-08-23 | Add individual sizes alongside combo sizes | Diya | Yes
T-010 | 2026-08-23 | Update all packing reports for all articles | Abhay | No
T-011 | 2026-08-23 | Update all BOM for all articles | Abhay | No
T-013 | 2026-08-23 | Send the packing report format | Abhay | No
T-014 | 2026-08-23 | Allow article-specific production plans in Catalogue | Diya | No
T-015 | 2026-08-23 | Add average dispatch days to MIS | Diya | Yes
T-016 | 2026-08-23 | Add dispatch shortage and order-vs-dispatch percentages | Diya | Yes
T-017 | 2026-08-23 | Show the MIS calculation logic | Diya | Yes
T-018 | 2026-08-23 | Add repair quantity capture and repair production planning before dispatch | Diya | No
T-019 | 2026-08-23 | Password-protect Machine Load | Diya | No
T-020 | 2026-08-23 | Show procurement shortfall against each PI | Diya | No
T-021 | 2026-08-23 | Allow article-specific production plans in Catalogue | Diya | No
T-022 | 2026-08-23 | Allow partial PI scheduling | Diya | No
T-023 | 2026-08-23 | Allow manual production-plan editing with warnings and override | Diya | No
21 Aug 2026 |  |  |  | 33 of 35 done
T-024 | 2026-08-21 | Create the management MIS dashboard | Diya | Yes
T-025 | 2026-08-21 | Fix order reading when one article has multiple size lines | Diya | Yes
T-026 | 2026-08-21 | Create the client input sheet for machines, live plans and actual production | Diya | Yes
T-027 | 2026-08-21 | Make Catalogue editable for all categories, including Gola Plus | Diya | Yes
T-028 | 2026-08-21 | Link scheduling to the PI database | Diya | Yes
T-029 | 2026-08-21 | Generate a PI after Match & Check edits | Diya | Yes
T-030 | 2026-08-21 | Require PI regeneration when checked data changes | Diya | Yes
T-031 | 2026-08-21 | Retain PI draft while changing tabs | Diya | Yes
T-032 | 2026-08-21 | Create a new PI after edits | Diya | Yes
T-033 | 2026-08-21 | Remove Party & Article Defaults from Match & Check | Diya | Yes
T-034 | 2026-08-21 | Keep customer and order fields on every article | Diya | Yes
T-035 | 2026-08-21 | Recalculate packing when article or type changes | Diya | Yes
T-036 | 2026-08-21 | Make Spike follow Armour packing | Diya | Yes
T-037 | 2026-08-21 | Show the packing list for every article and type | Diya | Yes
T-038 | 2026-08-21 | Show the BOM for every article and type | Diya | Yes
T-039 | 2026-08-21 | Edit pairs per carton in Packing & BOM Rules | Diya | Yes
T-040 | 2026-08-21 | Read the supplied Institutional and MTO order book | Diya | Yes
T-041 | 2026-08-21 | Read all workbook sheets and XLSM files in bulk upload | Diya | Yes
T-042 | 2026-08-21 | Use a one-row-per-article order template | Diya | Yes
T-043 | 2026-08-21 | Edit orders after saving a PI | Diya | Yes
T-044 | 2026-08-21 | Create a master PI database | Diya | Yes
T-045 | 2026-08-21 | Remove dispatch timeline from Parties & Terms | Diya | Yes
T-046 | 2026-08-21 | Remove the unnecessary one-day production buffer | Diya | Yes
T-047 | 2026-08-21 | Show production-planning logic for each order | Diya | Yes
T-048 | 2026-08-21 | Document Vercel and database deployment steps | Diya | Yes
T-049 | 2026-08-21 | Use party discount and payment terms on each PI | Diya | Yes
T-050 | 2026-08-21 | Allow order entry in cartons | Diya | Yes
T-051 | 2026-08-21 | Add Preparation between Cutting and Stitching | Diya | Yes
T-052 | 2026-08-21 | Choose in-house or outside stitching and capture printing | Diya | Yes
T-053 | 2026-08-21 | Add Upper QC between Stitching and Molding | Diya | Yes
T-054 | 2026-08-21 | Separate PVC Rotary, PVC Vertical, PU and Stuck-on machines | Diya | Yes
T-055 | 2026-08-21 | Separate Packing and Dispatch stages | Diya | Yes
T-056 | 2026-08-21 | Create dispatch reports and reduce pending quantity | Diya | Yes
T-057 | 2026-08-21 | Allow specific sizes on an article | Unassigned | No
T-058 | 2026-08-21 | Add Partial, Full and Shortage dispatch statuses | Unassigned | No

## Live Tracker
Factory OS Live Tracker
Total Tasks |  | Completed |  | Outstanding | Completion
58 |  | 45 |  | 13 | 77.59%
Use the dropdown in Done? to toggle each task between Yes and No. Filter the table to focus by date, owner, or status.
Task ID | Date | Change / Task | Owner | Done?
T-001 | 2026-08-26 | PI generation tab was wrong - reading sizing wrong, not able to edit PI blanks | Diya | Yes
T-002 | 2026-08-26 | Order dispatch not linked to other tabs | Diya | Yes
T-003 | 2026-08-26 | PI database tab errors - ability to delete, sync across tabs, etc. | Diya | Yes
T-012 | 2026-08-24 | Update catalogue images for all articles | Abhay | No
T-004 | 2026-08-23 | Add dispatch timeline option per order | Diya | Yes
T-005 | 2026-08-23 | Generate PI is not reloading to latest discount terms | Diya | Yes
T-006 | 2026-08-23 | Edit MRP should be size by size | Diya | Yes
T-007 | 2026-08-23 | Demo how to add BOMs, catalogue pictures and packing lists | Diya | Yes
T-008 | 2026-08-23 | Treat L as Large; keep Lace and Velcro separate | Diya | Yes
T-009 | 2026-08-23 | Add individual sizes alongside combo sizes | Diya | Yes
T-010 | 2026-08-23 | Update all packing reports for all articles | Abhay | No
T-011 | 2026-08-23 | Update all BOM for all articles | Abhay | No
T-013 | 2026-08-23 | Send the packing report format | Abhay | No
T-014 | 2026-08-23 | Allow article-specific production plans in Catalogue | Diya | No
T-015 | 2026-08-23 | Add average dispatch days to MIS | Diya | Yes
T-016 | 2026-08-23 | Add dispatch shortage and order-vs-dispatch percentages | Diya | Yes
T-017 | 2026-08-23 | Show the MIS calculation logic | Diya | Yes
T-018 | 2026-08-23 | Add repair quantity capture and repair production planning before dispatch | Diya | No
T-019 | 2026-08-23 | Password-protect Machine Load | Diya | No
T-020 | 2026-08-23 | Show procurement shortfall against each PI | Diya | No
T-021 | 2026-08-23 | Allow article-specific production plans in Catalogue | Diya | No
T-022 | 2026-08-23 | Allow partial PI scheduling | Diya | No
T-023 | 2026-08-23 | Allow manual production-plan editing with warnings and override | Diya | No
T-024 | 2026-08-21 | Create the management MIS dashboard | Diya | Yes
T-025 | 2026-08-21 | Fix order reading when one article has multiple size lines | Diya | Yes
T-026 | 2026-08-21 | Create the client input sheet for machines, live plans and actual production | Diya | Yes
T-027 | 2026-08-21 | Make Catalogue editable for all categories, including Gola Plus | Diya | Yes
T-028 | 2026-08-21 | Link scheduling to the PI database | Diya | Yes
T-029 | 2026-08-21 | Generate a PI after Match & Check edits | Diya | Yes
T-030 | 2026-08-21 | Require PI regeneration when checked data changes | Diya | Yes
T-031 | 2026-08-21 | Retain PI draft while changing tabs | Diya | Yes
T-032 | 2026-08-21 | Create a new PI after edits | Diya | Yes
T-033 | 2026-08-21 | Remove Party & Article Defaults from Match & Check | Diya | Yes
T-034 | 2026-08-21 | Keep customer and order fields on every article | Diya | Yes
T-035 | 2026-08-21 | Recalculate packing when article or type changes | Diya | Yes
T-036 | 2026-08-21 | Make Spike follow Armour packing | Diya | Yes
T-037 | 2026-08-21 | Show the packing list for every article and type | Diya | Yes
T-038 | 2026-08-21 | Show the BOM for every article and type | Diya | Yes
T-039 | 2026-08-21 | Edit pairs per carton in Packing & BOM Rules | Diya | Yes
T-040 | 2026-08-21 | Read the supplied Institutional and MTO order book | Diya | Yes
T-041 | 2026-08-21 | Read all workbook sheets and XLSM files in bulk upload | Diya | Yes
T-042 | 2026-08-21 | Use a one-row-per-article order template | Diya | Yes
T-043 | 2026-08-21 | Edit orders after saving a PI | Diya | Yes
T-044 | 2026-08-21 | Create a master PI database | Diya | Yes
T-045 | 2026-08-21 | Remove dispatch timeline from Parties & Terms | Diya | Yes
T-046 | 2026-08-21 | Remove the unnecessary one-day production buffer | Diya | Yes
T-047 | 2026-08-21 | Show production-planning logic for each order | Diya | Yes
T-048 | 2026-08-21 | Document Vercel and database deployment steps | Diya | Yes
T-049 | 2026-08-21 | Use party discount and payment terms on each PI | Diya | Yes
T-050 | 2026-08-21 | Allow order entry in cartons | Diya | Yes
T-051 | 2026-08-21 | Add Preparation between Cutting and Stitching | Diya | Yes
T-052 | 2026-08-21 | Choose in-house or outside stitching and capture printing | Diya | Yes
T-053 | 2026-08-21 | Add Upper QC between Stitching and Molding | Diya | Yes
T-054 | 2026-08-21 | Separate PVC Rotary, PVC Vertical, PU and Stuck-on machines | Diya | Yes
T-055 | 2026-08-21 | Separate Packing and Dispatch stages | Diya | Yes
T-056 | 2026-08-21 | Create dispatch reports and reduce pending quantity | Diya | Yes
T-057 | 2026-08-21 | Allow specific sizes on an article | Unassigned | No
T-058 | 2026-08-21 | Add Partial, Full and Shortage dispatch statuses | Unassigned | No