## Changes
Date | Changes discussed | Task for | Made yet?
23rd Aug | Add dispatch timeline option per order | Diya | Yes
23rd Aug | Generate PI is not reloading to latest discount terms | Diya | Yes
23rd Aug | Edit MRP should be size by size | Diya | Yes
23rd Aug | Demo how to add BOMs, catalogue pictures and packing lists | Diya | Yes
23rd Aug | Treat L as Large; keep Lace and Velcro separate | Diya | Yes
23rd Aug | Add individual sizes alongside combo sizes | Diya | Yes
23rd Aug | Update all packing reports for all articles | Abhay | No
23rd Aug | Update all BOM for all articles | Abhay | No
24th Aug | Update catalogue images for all articles | Abhay | No
23rd Aug | Send the packing report format | Abhay | No
23rd Aug | Allow article-specific production plans in Catalogue | Diya | No
23rd Aug | Add average dispatch days to MIS | Diya | Yes
23rd Aug | Add dispatch shortage and order-vs-dispatch percentages | Diya | Yes
23rd Aug | Show the MIS calculation logic | Diya | Yes
23rd Aug | Add repair quantity capture and repair production planning before dispatch | Diya | No
23rd Aug | Password-protect Machine Load | Diya | No
23rd Aug | Show procurement shortfall against each PI | Diya | No
23rd Aug | Allow article-specific production plans in Catalogue | Diya | No
23rd Aug | Allow partial PI scheduling | Diya | No
23rd Aug | Allow manual production-plan editing with warnings and override | Diya | No
21st Aug | Create the management MIS dashboard | Diya | Yes
21st Aug | Fix order reading when one article has multiple size lines | Diya | Yes
| Create the client input sheet for machines, live plans and actual production | Diya | Yes
| Make Catalogue editable for all categories, including Gola Plus | Diya | Yes
| Link scheduling to the PI database | Diya | Yes
| Generate a PI after Match & Check edits | Diya | Yes
| Require PI regeneration when checked data changes | Diya | Yes
| Retain PI draft while changing tabs | Diya | Yes
| Create a new PI after edits | Diya | Yes
| Remove Party & Article Defaults from Match & Check | Diya | Yes
| Keep customer and order fields on every article | Diya | Yes
| Recalculate packing when article or type changes | Diya | Yes
| Make Spike follow Armour packing | Diya | Yes
| Show the packing list for every article and type | Diya | Yes
| Show the BOM for every article and type | Diya | Yes
| Edit pairs per carton in Packing & BOM Rules | Diya | Yes
| Read the supplied Institutional and MTO order book | Diya | Yes
| Read all workbook sheets and XLSM files in bulk upload | Diya | Yes
| Use a one-row-per-article order template | Diya | Yes
| Edit orders after saving a PI | Diya | Yes
| Create a master PI database | Diya | Yes
| Remove dispatch timeline from Parties & Terms | Diya | Yes
| Remove the unnecessary one-day production buffer | Diya | Yes
| Show production-planning logic for each order | Diya | Yes
| Document Vercel and database deployment steps | Diya | Yes
| Use party discount and payment terms on each PI | Diya | Yes
| Allow order entry in cartons | Diya | Yes
| Add Preparation between Cutting and Stitching | Diya | Yes
| Choose in-house or outside stitching and capture printing | Diya | Yes
| Add Upper QC between Stitching and Molding | Diya | Yes
| Separate PVC Rotary, PVC Vertical, PU and Stuck-on machines | Diya | Yes
| Separate Packing and Dispatch stages | Diya | Yes
| Create dispatch reports and reduce pending quantity | Diya | Yes
Allow specific sizes on an article
Add Partial, Full and Shortage dispatch statuses
Note on D8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Due to model bugs